| Implementation Plan |  |  |  |
| --- | --- | --- | --- |
| Policy name: | PUBLIC HEALTH WALES research misconduct POLICY |  |  |
| Ref no: | PHW 73 |  |  |
| Subject area: | Research |  |  |
| Accountable Executive Director/Director | Director of Knowledge/ Transition Director |  |  |
| Author: | Mark Griffiths, Laura Evans, Alisha Davies |  |  |
| Version | 1 | Date: | 18.11.2019 |

| Implementation plan (with timescales) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Timescale | Next steps |  | Responsible officer(s) |  |  |
| Quarter 3 2019-20 (Baseline) | 30 day consultation |  | Alisha Davies |  |  |
|  | Collation of responses and necessary amendments made |  |  |  |  |
|  | Launch of new policy |  |  |  |  |
| Quarter 4 2019-20 (Baseline) | Monitor implementation of policy |  | John Lawson, Alisha Davies, Sian Bolton |  |  |
|  | Record number of incidents requiring a response to an allegation of research misconduct by each quarter |  | John Lawson, Mark Griffiths |  |  |
|  | Report any new cases to the R&E Oversight Group and BET, KRIC as appropriate |  | Sian Bolton, Alisha Davies |  |  |
| Quarter 1 2020-21 (Baseline) | Continued monitoring and reporting |  | John Lawson, Alisha Davies, Sian Bolton |  |  |
|  | Report any new cases to the R&E Oversight Group and BET, KRIC as appropriate |  | Sian Bolton, Alisha Davies |  |  |
| Quarter 4 2020-21 (Baseline) | Continued monitoring and reporting |  | John Lawson, Alisha Davies, Sian Bolton |  |  |
|  | Review policy implementation at the end of year 1 with R&E Oversight Group |  | Mark Griffiths, Alisha Davies |  |  |
|  | Make any necessary alterations and notify Corporate Governance, BET and KRIC |  | Alisha Davies, Sian Bolton |  |  |
| Feedback |  |  |  |  |  |
| Amendments required to policy |  |  |  |  |  |
| Completed by: |  | Mark Griffiths |  | Date: | 18.11.2019 |
| Board/Committee approval: |  |  |  | Date: | 06.02.2020 |