## Sheet1
RAG Rating Guide
Red | Red - Action date passed - action not complete
Orange | Orange - Action not on target for completion by agreed/revised date
Yellow | Yellow - Action on target to be completed by agreed/revised date
Green | Green- Action complete
Blue | Blue - Action to be removed and replaced by subsequent action
Meeting | Date Raised / Action Ref | Action | Update | Original Target Date | Revised Target Date | RAG Rating | Lead | Status (Open or Complete)
Board Meeting | 30/07/2020 PHW123/2020 Presentation - Focus on Sampling and Testing | RH outlined the actions being taken to mitigate against this and agreed to supply a briefing for Board members on this issue. | Briefing in progress, will be circulated end of week commencing 21 September 2020 |  |  |  | RH | Open
Completed actions to be approved by the Board
Board Meeting | 30/07/20 PHW125/2020 Chief Executive's Report | In the absence of KRIC meetings, SG would continue to brief the Board on key issues | Updates will be provided as appropriate. Action proposed to be closed on basis updates will be produced as required. |  |  |  | SB | Complete
Board Meeting | 30/07/2020 PHW129/2020 Novel Coronavirus (COVID-19) General Update | AW reflected on the swift mobilisation of the contact tracing function across Wales and the potential to do more, if the system moved to testing on symptoms, rather than on a positive test. She noted that Public Health Wales had advocated this, asked if that remained the case, and what the progress was. QS confirmed that this remained the Public Health Wales’ position; the TTP programme Board was of the view that the system was not yet ready to make this move; discussions continued and he would keep the Board updated | Updates will be provided as appropriate. Action proposed to be closed on basis updates will be produced as required. |  |  |  | QS | Complete
Board Meeting | 30/07/2020 PHW130/2020 Workforce - Our People | The Business Executive Team intended to take stock of the People Strategy implementation plan and update it, to reflect the organic changes that had already taken place. | Stock take of the People Strategy added to Business Execuitve Team |  |  |  | RB-W/NL | Complete
Board Meeting | 30/07/2020 PHW 133/2020 Committees of the Board | Audit and Corporate Governance Committee the Committee to consider oversight of any additional resource needed for winter pressures; this would align with oversight of COVID-related expenditure. DE and HG agreed to this request, with HG also confirming the intention to incorporate all costs associated with the Stage 3 Implementation Plan and service reactivation plans into one complete, resourced plan for Board consideration. | Item will be considered at the Audit and Corporate Governance Committee; Operating Plan will also be considered by Board at the October meeting. |  |  |  | DE/HG | Complete
Board Meeting | 30/07/2020 PHW 135/2020 Items for Noting | HB agreed to incorporate the feedback into the Board forward plan | Feedback incorporated into forward plan |  |  |  | HB | Complete