|  |  |  |  | Name of Meeting Board |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Date of Meeting 28 January 2021 |  |  |
|  |  |  |  | Agenda item: 3.3 280121 |  |  |
| 2020/21 Financial Position |  |  |  |  |  |  |
| Executive lead: |  | Huw George, Deputy Chief Executive and Executive Defector of Finance and Operations |  |  |  |  |
| Author: |  | Angela Fisher, Deputy Director and Head of Finance Ruth Maddern, Head of Financial Management & Business Partnering Suzanne David, Senior Finance Business Partner |  |  |  |  |
| Approval/Scrutiny route: |  | Huw George, Deputy Chief Executive and Executive Director of Finance and Operations Business Executive Team – 18 January 2021 |  |  |  |  |
| Purpose |  |  |  |  |  |  |
| The purpose of this report is to outline to the Executive Team and the Board the revenue and capital position for Public Health Wales as at 31st December 2020, which includes the position on COVID-19. |  |  |  |  |  |  |
| Recommendation: |  |  |  |  |  |  |
| APPROVE | CONSIDER |  | RECOMMEND |  | ADOPT | ASSURANCE |
| The Board is asked to consider the following: - A surplus financial position of £36k, along with the assumed allocations, reported at month 9; - A forecast year-end break-even position, which includes the month 10 to month 12 projections for Covid-19 testing capacity; - Status of the Capital Programme, strategic and discretionary, for 2020/21, and - Balance Sheet, or Statement of Financial Position, which includes the cash balance of £1.6m at month 9. |  |  |  |  |  |  |

- Introduction and Context

The purpose of this report is to outline to the Executive Team and the Board the revenue and capital position for Public Health Wales as at 31st December 2020 (M9). The report is also circulated to the Audit and Corporate Governance Committee. The content of this report is reflected in the Director of Finance commentary that has been submitted to Welsh Government on 14th January 2020 as part of the full financial monitoring return for Month 9.

The following table highlights the performance against the key revenue and capital financial targets.

| Target | Current Month | Year to Date | Year-end Forecast |
| --- | --- | --- | --- |
| Revenue financial target Deficit/(Surplus) | (13K) | (36K) | Breakeven |
| Capital financial target | 1.489m | 1.181m | Breakeven |
| Public Sector Payment Policy | 97% | 96.33% | >95% |

The Public Health Wales financial position as at 31st December is a net surplus of £36k. This position includes £28.906m of costs directly related to the COVID-19 response, of which:

- £2.077m has been met from within Public Health Wales budgets to cover the following costs as follows:

  - £857k from pay underspends;

  - £1.136m from non-pay reductions in spend and internal investment slippage, and

  - £193k from the re-purposing of the investment funding from the National Health Protection Service.

- £495k has been met from external funding in respect of Genomics sequencing tests and platform validation, with

- £26.334m of additional funding from Welsh Government covering:

  - Pay (Quarters 1 & 2) £2.330m;

  - Testing strategy £21.637m;

  - Genomics sequencing £1.127m;

  - IP5 Laboratory Pay £0.310m;

  - Hot Laboratory, Resilience and improved turnaround times Pay £0.358m;

  - Flu Programme £0.083m;

  - £0.365m Online Testing for STIs, and

  - Institute of Clinical Science and Technology PPE guidance £0.124m.

- Overview of Financial Performance at Month 9

  - Financial Performance by Directorate

Table A outlines the Financial Performance by Directorate and the Covid-19 response.

Table A – Overview of Financial Performance by Directorate

| Directorate | Income Variance £000s | Pay Variance £000s | Non Pay Variance £000s | Total £000s |
| --- | --- | --- | --- | --- |
| Public Health Services | 519 | 86 | -387 | 218 |
| Central Budgets | 28 | 190 | -59 | 160 |
| Board and Corporate | 0 | -9 | 9 | 0 |
| ACE's Hub | 0 | 0 | 0 | 0 |
| Hosted | 0 | 0 | 0 | 0 |
| Population Health | 0 | 0 | 0 | 0 |
| Improvement Cymru | -1 | -5 | 0 | -6 |
| WHO Collaborating Centre | 0 | -17 | -9 | -26 |
| Quality Nursing & Allied Health Professionals | 0 | -27 | -4 | -31 |
| Operations and Finance | 0 | -61 | 9 | -52 |
| Knowledge | 0 | -38 | -21 | -60 |
| People & Organisational Development | 0 | -22 | -51 | -73 |
| Health & Wellbeing | 1 | -69 | -99 | -167 |
| Directorate Total | 548 | 28 | -612 | -36 |
| COVID 19 | -12 | -360 | 372 | 0 |
| COVID19 Total | -12 | -360 | 372 | 0 |
| Grand Total | 536 | -332 | -240 | -36 |

The main variance at Month 9 is within Public Health Services. Microbiology division has overspent to month 9 by £1.653m, mainly due to the underachievement against income targets and pay pressures in medical staffing in North Wales.  The overspend has been partially offset by underspends in Screening division of £864k, Health Protection division of £415k, SPR Division of £112k and Public Health Services Corporate division of £43k resulting in a net Directorate month 8 overspend of £219k.  These underspends are in the main due to slippage on recruitment to established posts. Public Health Services Directorate will continue to work towards an overall year-end break-even plan.

2.2 Assumed Welsh Government Allocations

The monitoring return submitted to Welsh Government includes the request for additional allocation to support the following costs included within the month 9 position:-

Table B – Assumed Welsh Government Allocations

| Theme/Area | Pay | Non Pay | Anticipated Allocation £m |
| --- | --- | --- | --- |
| Early Years Prevention | 0.136 | 0.032 | 0.168 |
| Digital Strategy | 0.181 | 0.019 | 0.200 |
| Grand Total | 0.317 | 0.051 | 0.368 |

Early Years Prevention

£168k of costs have been incurred to month 9 on initiatives associated with Early Years Prevention. During month 9, we have had confirmation from Welsh Government that funding will be provided for Early Years prevention based on actual costs incurred during 2020/21.

Digital Strategy

£200k of costs have been incurred to month 9 as a result of recurrent digital commitments that were part of our digital strategy bid in 2019/20.  The allocation is included as an assumed allocation in 2020/21 and is still outstanding from Welsh Government, it is therefore included within our month 9 funding request.

2.3 Budget Scrutiny

Following the income and expenditure budget scrutiny process, which was approved by the Business Executive Team, Directorate budgets have been realigned to match Directorate spending plans.  Budget slippage identified in the scrutiny process has been re-allocated to fund the Public Health Wales contribution to the costs associated in delivering the response to Covid-19, including work associated with Population Health Priority.

Month 10-12 spending plans will be monitored against the re-aligned budgets.  Future slippage against these spending plans may be removed to support additional requirements associated with delivery of the response and essential services.

Welsh Government have agreed to fund a significant element of additional Covid-19 response costs incurred by Public Health Wales, with funding from slippage/underspends within Public Health Wales also being redirected to support an element of the Covid-19 response costs.

2.4 Status of Long Term/Service Level Agreements

As a result of the Covid-19 pandemic, All Wales Directors of Finance initially agreed a funds flow approach for quarters 1 and 2 that was on the premise of keeping NHS Wales operating through giving stability to providers with the financial risk and significant opportunity costs sitting with commissioners.  For Public Health Wales this meant that NHS LTAs and SLAs were essentially “block” agreements and would not generate a performance cost variation.  This agreement has been extended for the remainder of this financial year.

2.5 Savings/Organisational Efficiencies

Public Health Wales savings strategy for 2020/21, as set out in the IMTP, was £1.350m, made up of 1% Directorate savings £900k and 0.5% Organisational Efficiencies £450k.

Of the £900k relating to the 1% savings target assigned to each Directorate, £74k was met by increased vacancy factors, £75k from changes within staffing establishments, non-pay efficiencies of £670k and delivery of income generation schemes totalling £80k.

Of the £450k relating to Organisational efficiencies, £120k related to savings linked to VERs in 2019/20 and was achieved in month 1.  The remaining efficiencies were linked to £105k procurement efficiencies, £40k Salary Sacrifice Schemes and £185k unidentified (red schemes).  Due to COVID-19 priorities, these have all now been re-classified as red schemes.

2.6 Investments

There has been slippage against investments within Public Health Wales due to delays in the allocation of internal investment funding as a result of COVID-19.

Due to the inability of our Directorates to pursue their original investment plans, £964k of month’s 1 – 9 investment slippage has been used to form part of Public Health Wales overall financial commitment to supporting the COVID-19 response. The investment monies have been built into Public Health Wales revised Operational plans and forecast breakeven position.

- Forecast position

3.1 Covid-19

NHS Wales organisations are required to submit a COVID19 monitoring return as part of their Monthly Monitoring Returns to Welsh Government. This captures a forecast for all COVID-19 costs for 2020/21 along with non-delivery of planned savings, planned operational expenditure cost reductions and slippage on planned investments.

Appendix 1 includes the full monitoring return submitted by Public Health Wales on 14 January 2021.  Table B3 within the return specifically relates to COVID-19.  Actual costs have been reported for April to December 2020 and estimated costs have been included for January through to March 2021.  It has been assumed that Welsh Government will fund the remaining COVID-19 expenditure over and above internal funding already identified.

Table C summarises the operational expenditure and funding source of the Public Health Wales Covid-19 response plan:

Table C – Covid-19 financial forecast at month 9

Actual costs for Antigen testing have been reported for April through to December 2020.  Samples received to December for testing in Welsh laboratories have not exceeded 50% of the capacity available and therefore the forecast for Q4 has been reduced based on the assumption that the current levels of testing in Welsh laboratories will continue.  Estimated costs for January through to March 2021 are based on the following testing numbers:

|  | Jan-20 | Feb-20 | Mar-20 |
| --- | --- | --- | --- |
| Tests per day | 5,000 | 5,000 | 5,000 |
| Total monthly tests | 155,000 | 140,000 | 155,000 |

There is an assumption that 300 tests per day are funded through UK allocation from Roche and the remaining are undertaken on a mix of other platforms.  This includes current platforms plus the additional platforms now operational within ‘Hot’ laboratories.  Actual costs will be influenced by any changes to the UK allocation and by the future testing requirements for NHS Wales laboratories.

The original plan was for Public Health Wales to provide capacity for antibody testing to be undertaken in the IP5 laboratory.  Welsh Government approved a contract with Ortho Clinical Diagnostics for the supply of testing kits to deliver this capacity.  Due to a change in Welsh Government policy on antibody testing Public Health Wales are working with Ortho Clinical Diagnostics to verify and validate the kits for use as antigen testing kits.  No additional costs have been included in the forecast for antibody testing.

3.2 All other Directorates

Following the income and expenditure budget scrutiny process a breakeven position has been forecasted for Public Health Wales.  This includes an assumption that Welsh Government will fund the remaining COVID-19 expenditure over and above internal funding already identified.

There remains a clear finance focus on the response, reactivation of essential services and other priorities to ensure underlying financial balance is maintained within the parameters of the Board approved budget for 2020/21.

- Capital

Public Health Wales capital funding for 2020/21 totals £11.910m, with £0.400m unapproved contingency held for IP5, summary of the schemes detailed in Table D.

| Fund | Details | 2020/21 Allocation £000's | YTD Spend 2020/21 £000's |
| --- | --- | --- | --- |
| Discretionary | COVID 19 various | 160 | 153 |
| Discretionary | Screening Mobile upscale - Recovery following COVID-19 | 57 | 58 |
| Discretionary | Matrix Heating system control mechanism (b/f form 19/20) | 12 | 0 |
| Discretionary | CSIMS Cervical information system NHAIS replacement | 281 | 218 |
| Discretionary | Contingency | 99 | 0 |
| Discretionary | IT - New laptops/desktops/ replacement | 511 | 11 |
| Discretionary | Retinal Image Management System Optpmize Software Support - DESW | 25 | 0 |
| Discretionary | Replacement of virtual infrastructure at CQ2 | 266 | 0 |
| Discretionary | LINC (£58k re provided from 19/20) | 58 | 58 |
| Discretionary | Screening - Replacement Generators and biopsy chair | 48 | 8 |
| Discretionary | Replacement dated lighting systems with LED lighting systems | 24 | 24 |
| Discretionary | Class 1 safety cabinet replacement x 6 (Cardiff x4, Carmarthen x 1, Bangor x 1) | 146 | 0 |
| Discretionary Total |  | 1,687 | 530 |
| Strategic | Cepheid Systems | 718 | 718 |
| Strategic | Eplex | 553 | 553 |
| Strategic | PerkinElmer Platforms & Reagents | 740 | 740 |
| Strategic | Hot Labs & Laboratory Resilience | 2,365 | 1,718 |
| Strategic | MAST 3 x Microlab Startlet, optical Unit and thermal cylinder | 429 | 429 |
| Strategic | Imperial Park 5 | 4,000 | 4,676 |
| Strategic | MAST Seegene | 666 | 672 |
| Strategic | LINC | 752 | 376 |
| Strategic Total |  | 10,223 | 9,882 |
| PHE Grant | Additional genome sequencing | 26 | 0 |
| Total Approved Schemes |  | 11,936 | 10,413 |
| Strategic (Unapproved) | Imperial Park 5 - contingency | 400 | 0 |
| Total Schemes (Approved & Unapproved) |  | 12,336 | 10,413 |

Public Health Wales discretionary allocation of £1.687m remains the same as previous years.  Allocation of this to specific programmes was approved by Business Executive Team in July 2020. An updated Capital paper was submitted to the Business Executive on the 15 December 2020, where approval was given for additional capital schemes and which are reflected in the table above.

PHW Strategic allocation for 20/21 of £10.223m is predominantly driven by the response to COVID-19.

Of the £4.676m YTD capital expenditure for PHW laboratory capacity at Imperial Park 5 £0.826m reflects the spending on the original laboratory built at Imperial Park 5, which has now transferred to DHSC. These costs will be recovered from DHSC.

A grant has been awarded by Public Health England relating to additional genome sequencing during the winter months, £0.026m of which will be used to purchase capital items.

- Balance Sheet

The Balance Sheet, or Statement of Financial Position, reports the assets, liabilities and reserves of the organisation at a specific point in time. Table E provides a summary as at 31st December 2020.

Table E – Balance Sheet as at 31st December 2020

| ` | Opening Balance 1/4/2020 £000s | Movement £000s | Closing Balance 31/12/20 £000s |
| --- | --- | --- | --- |
| Non-Current Assets |  |  |  |
| Property, plant and equipment | 11,941 | 8,727 | 20,668 |
| Intangible assets | 1,334 | (237) | 1,097 |
| Trade and other receivables | 0 | 0 | 0 |
| Non-Current Assets sub total | 13,275 | 8,490 | 21,765 |
| Current Assets |  |  |  |
| Inventories | 866 | 10,313 | 11,179 |
| Trade and other receivables | 14,379 | 21,753 | 36,132 |
| Cash and cash equivalents | 8,819 | (7,226) | 1,593 |
| Current Assets sub total | 24,064 | 24,840 | 48,904 |
| TOTAL ASSETS | 37,339 | 33,330 | 70,669 |
| Current Liabilities |  |  |  |
| Trade and other payables | (18,898) | (26,828) | (45,726) |
| Provisions | (1,206) | (744) | (1,950) |
| Current Liabilities sub total | (20,104) | (27,572) | (47,676) |
| NET ASSETS LESS CURRENT LIABILITIES | 17,235 | 5,758 | 22,993 |
| Non-Current Liabilities |  |  |  |
| Trade and other payables | (1,381) | (283) | (1,664) |
| Provisions | (1,291) | 41 | (1,250) |
| Non-Current Liabilities sub total | (2,672) | (241) | (2,914) |
| TOTAL ASSETS EMPLOYED | 14,563 | 5,516 | 20,079 |
| FINANCED BY: Taxpayers' Equity |  |  |  |
| PDC | 13,444 | 5,423 | 18,867 |
| Retained earnings | 609 | 34 | 643 |
| Revaluation reserve | 510 | 58 | 568 |
| TOTAL TAXPAYERS' EQUITY | 14,563 | 5,516 | 20,079 |

Non-Current Assets

Property, plant and equipment has increased overall by £8.727m, the majority of which relates to Covid-19 projects.  This reflects the net position of our capital purchases to month 9.

Current Assets

Stock has increased by £10.313m due to purchases of Covid-19 consumables for laboratories and testing facilities.  We expect the stock balance to continue to decrease over the coming months as testing progresses.

Trade and other receivables has increased by £21.753m. This increase is predominantly on Whole of Government Accounts receivables, Welsh Government Covid-19 funding of £4.447m and the core income invoice of £8.860m for January, which is raised a month in advance. NHS Wales Health Collaboratives core income allocation of £6.012m and £3.500m for Welsh Government Implementation Group Delivery Plan income.

Cash has reduced by £7.226m due to increased high value payments relating to Covid-19 during December.  These were expected and the cash position is being monitored routinely.

Current liabilities

Current trade and other payables has increased by £26.828m.  Welsh Government deferred core income of £14.377m is included in this balance relating to baseline core income raised a month in advance £13.800m and capital charges £0.577m.  There are also significant accruals in relation to purchase orders for Covid-19 consumables £3.142m.  Other significant accruals include £0.880m for Capital creditors, £3.246m for pay and non-pay expenditure accruals within the NHS Wales Health Collaborative, £0.037m for the NWSSP 365 rollout and £2.556m for Health & Wellbeing accruals for NERS and Healthy Schools scheme.

The increase in provisions of £0.744m is primarily due to 3 new clinical negligence cases in June 20/21.  The Trust is only liable for £75k of the increase in provision, the first £25k of payments on each case, with the remainder being reimbursed by the Welsh Risk Pool.

PDC

The Public Dividend Capital (PDC) balance has increased by £5.423m since the beginning of the year. Welsh Government has provided upfront PDC to fund the build of the laboratory at Imperial Park, Newport as well as other Covid-related capital purchases.

- Procurement Activity and Supply Chain

The Audit and Corporate Governance Committee are provided with a report on procurement activity in accordance with paragraph 1.2.1 and Schedule 1 of the SFIs.  This includes an explanation of the reasons and circumstances for Single Quotation Action and Single Tender Action along with the further action taken.

As part of the Sampling and Testing activity a Laboratory Rapid Implementation Programme Board was established to track progress on the increased capacity and monitor impact of any supply chain issues.  The Programme Board provide regular updates to Business Executive Team and appropriate escalation to Board as necessary.

Conclusion

The Board is asked to consider the following:

- A surplus financial position of £36k, along with the assumed allocations, reported at month 9;

- A forecast year-end break-even position, which includes the month 10 to month 12 projections for Covid-19 testing capacity;

- Status of the Capital Programme, strategic and discretionary, for 2020/21, and

- Balance Sheet, or Statement of Financial Position, which includes the cash balance of £1.6m at month 9.