Risk Owner’s Overview Assessment Status

The refresh of our Long Term Strategy (LTS) has taken into account the current and emerging threats, as we know them to be, and these are reflected in the strategic priorities. Work is underway to review the strategic risks in relation to the priorities. We have had a number of meetings with the CMO and colleagues in relation to the priorities, to include a Government view. Considerable work continues in relation to the cost of living, crisis including the joint running of a Wales Cost of Living Summit with the Building a Healthier Wales Coordination Group including all sectors and partners. Sumina Azam continues to represent us on the Cost of Living Expert Group reporting to Cabinet. We continue to engage and support Ukraine through IANPHI. We are concluding a health impact assessment on the impact of climate change on health. This strategic risks are being reviewed as part of the new LTS and this risk will be reviewed as to whether it is still required.

| Risk 1 | There is a risk that Public Health Wales will not be sufficiently focused, agile and responsive in discharging our functions, caused by the unpredictable and changing nature of the current and emerging geopolitical, socio-economic and health threats, resulting in an inability to tackle the population health challenges in a sustainable way. |
| --- | --- |

| Sponsor and Assurance Group |  |
| --- | --- |
| Executive Sponsor | Tracey Cooper |
| Assuring Group | Quality, Safety and Improvement Committee |

| Inherent Risk |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date | 10.05.2022 | Likelihood: | 4 | Impact: | 4 | Score: | 16 |

| Risk Score |  |  |  |  |  | Risk Decision | Delivery Confidence Assessment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Current Risk |  |  | Target risk |  |  | Treat | Amber |
| Likelihood | Impact | 12 | Likelihood | Impact | 12 |  |  |
| 3 | 4 |  | 3 | 4 |  |  |  |

| EXISTING CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 1.1 | Regular Business Executive Team Meetings to review implementation of IMTP and emerging threats | Chief Executive/All Execs | Business Executive Team Minutes |  |  | X | X | X |
| SR 1.2 | Embedded management of health protection response for COVID within HPSS Directorate Leadership Team | National Director of Screening and Health Protection Services and Medical Director | Health Protection and Screening Services Directorate Leadership Team meeting minutes, and COVID Executive meeting minutes |  | X | X |  |  |
|  |  |  | COVID-Executive meeting minutes |  | X |  |  |  |
| SR 1.3 | Incident Management Teams in place for Ukraine conflict in PHW and in UK Health Security Agency for UK | National Director of Screening and Health Protection Services and Medical Director | Minutes of Incident Management Team and summary |  | X |  |  |  |
|  |  |  | Minutes of UK Health Security Agency Incident Management Team and summary |  | X | X |  |  |
| SR 1.4 | Regular meetings with Welsh Government Minister(s) and officials which include discussions in relation to existing and emerging health and socio-economic threats in Wales | Chief Executive | Actions arising following meetings as appropriate |  | X | X |  |  |
| SR 1.5 | Formalised meetings with WHO Collaborating Centre and WHO | Director of Policy Research and Development, Policy, Research and International Development | Minutes of WHO Collaborating Centre and WHO meetings |  |  |  |  |  |
| SR 1.6 | Weekly meetings with a number of International Association of National Public Health Institutes (IANPHI) European Institutes and Ukraine Public Health Institute | Chief Executive/ Director of Policy, Research and International Development | Notes of meetings at Executive Lead/ Business Executive Team level as appropriate. THESE HAVE NOW CEASED AND ARE INCORPORATED INTO A MORE GENERAL ENGAGEMENT |  |  |  |  |  |

| Action Plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 1.1 | Longer term planning for new and emerging threats incorporated into a revised Long Term Strategy to develop a coherent and synergistic approach to multi-shocks. |  | Development and approval of new Long Term Strategy | Deputy Chief Executive, Executive Director Operations and Finance | April 2023 | Update March 2023, the proposed LTS has continued to be develop with staff and Welsh Government engagement, with the development of the Strategic Plan (IMTP), for the first three years implementation of the LTS. These will be considered at the March board meeting. |
| AP 1.2 | More formalised series of collective public health ‘threat’ assessment to include health, environmental, socio-economic and geopolitical threats, to be incorporated into Strategic Business Executive Team business. |  | To be considered by BET with the view of identifying a lead (s) Exec to coordinate a regularised approach to multi-shock public health threat assessment – including domestic and global population health threats. | Chief Executive | Completed | Update March 2023. A wide range of population health activities, mitigating actions and consideration of threats continue to be considered by the Executive Team – at the business Executive and Strategy Team meetings. Meng Khaw and the HPSS team, continue to be connected to the four nations mechanisms on threats to health from infection and environmental issues. |
|  |  |  | Develop a rapid re-prioritisation planning process if required that is triggered by significant threats that require substantial in-year focus/resource | Deputy Chief Executive, Executive Director Operations and Finance | Completed | Update March 2023, this is an ongoing surveillance activity for us. The population health dashboard continues to be developed and will enable a more focused tracking of the population’s health at a national level. The WHOCC international horizon scanning reports continue, together with WHOCC and IANPHI relations, to enable surveillance of global threats. Collectively, these will enable us to consider any re-prioritisation required in-year after the new LTS and Strategic Plan commence. |
|  |  |  | Joint meetings with Welsh Government colleagues to consider this with inclusion of international partners as appropriate | National Director Health Protection and Screening Services, Executive Medical Director and Director of Policy Research and Development, Policy, Research and International Development | Actioned according to the threat and timing. Cost of living complete. | Update March 2023. This continues with regular meetings with the CMO including monthly joint strategic meetings. Close working continues with the WHO and IANPHI. |
| AP 1.3 |  |  | International Horizon Scanning reports to consider new and emerging global public health threats no less than twice a year | Director of Policy Research and Development, Policy, Research and International Development | Ongoing horizon scanning. Focus on emerging threats to be confirmed. | This is an ongoing and proactive series as issues and concerns arise. |

| Risk 2 | There is a risk that Public Health Wales will not deliver its plans for delivering excellent services for population screening, health protection and infection caused by uncertainty of the impact of current and future health threats and lack of specialist workforce, resulting in inability to prioritise service delivery and transform models of care. |
| --- | --- |

Risk Owner’s Overview Assessment Status

The current risk score is at the inherent risk level. However, in recent months, this had the potential to be higher resulting from a number of significant health protection incidents had increased (such as monkeypox, the exceedance of STEC and group A streptococcal infections), but those threats have now stabilised. There are existing controls relating to: workforce planning and development; mitigation of impacts of unexpected health threats through the establishment of effective systems and processes; and strengthening governance arrangements to ensure excellent service delivery in HPSS. Each of the three divisions in HPSS directorate are likely to score differently if reviewed independently and this will be reflected in divisional and directorate risk registers. This is a known dynamic risk and as such will be actively monitored and managed in HPSS at both division and directorate levels, all informing the strategic RR. As we look to the 2023 / 24 planning cycle this risk is likely to endure and the action plans during this months review reflect dates into next year. Reviewed February 2023

| Sponsor and Assurance Group |  |
| --- | --- |
| Executive Sponsor | National Director Health Protection and Screening Services, and Medical Director |
| Assuring Group | Quality, Safety and Improvement Committee |

| Inherent Risk |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date | 11.05.2022 | Likelihood: | 3 | Impact: | 3 | Score: | 9 |

| Risk Score |  |  |  |  |  | Risk Decision | Delivery Confidence Assessment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Current Risk |  |  | Target risk |  |  | Treat | Green |
| Likelihood | Impact | 9 | Likelihood | Impact | 6 |  |  |
| 3 | 3 |  | 3 | 2 |  |  |  |

| EXISTING CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 2.1 | Overview and scrutiny of workforce capacity and capability is provided through clear governance arrangements with divisional SMTs and DLT | National Director Health Protection and Screening Services, and Medical Director | Divisional SMT meeting and minutes | X | X |  |  |  |
|  |  |  | DLT meetings and minutes |  | X |  |  |  |
|  |  |  | Escalation to BET with meetings and minutes |  | X | X |  |  |
|  |  |  | Divisional, Directorate and Corporate Risk Registers actively updated and risks escalated as appropriate | X | X | X | X | X |
| SR 2.2 | Implementation of Business Continuity Arrangements where required and where appropriate | National Director Health Protection and Screening Services, and Medical Director | Business Continuity Action Plans for HPSS divisions | X | X | X |  |  |
|  |  |  | Emergency Planning and Business Continuity Group Meeting minutes |  | X |  |  |  |
|  |  |  | Training and Exercise reports to Emergency Planning and Business Continuity Group | X | X |  |  |  |
|  |  |  | Emergency Planning and Business Continuity Documentation (regular review and update) | X | X |  | X |  |
|  |  |  | Ability to sustain response to health threats |  | X |  |  |  |
| SR 2.3 | Utilisation and development of Policies and Procedures to enable effective and efficient service delivery, including Standard Operating Procedures and Protocols. | National Director Health Protection and Screening Services, and Medical Director | Corporate Policy and Control Document Reviews – corporate register update reports | X | X | X | X | X |
|  |  |  | Health Protection Division – Standard Operating Procedures (document development, review and approval) | X | X |  |  |  |
|  |  |  | Infection Division – Standard Operating Procedures (document development, review and approval), alignment to UKAS accreditation requirements. | X | X | X | X |  |
|  |  |  | Screening Division –For each of the screening programmes - Standard Operating Procedures (document development, review and approval) | X | X |  |  |  |
|  |  |  | Reports to Quality, Safety and Improvement Committee |  | X | X | X |  |
|  |  |  | Action Plan and Reports – Divisional Senior Management Teams | X |  |  |  |  |
| SR 2.4 | Uphold high professional standards: Professional Regulation – Medical, Nursing and Multi-Disciplinary Staff | National Director Health Protection and Screening Services, and Medical Director | Medical, Nursing and Multi-Disciplinary Staff Revalidation - Annual Report to People and Organisational Development Committee / Quality, Safety and Improvement Committee |  |  |  | x |  |
|  |  |  | Quality review visit by Medical and Multi-Disciplinary Revalidation support unit |  |  | X | X |  |
|  |  |  | Quality Indicators Performance Monitoring | X | X | X | X |  |
|  |  |  | Monitor Specialist Registration and Revalidation |  | X | X | X | X |
|  |  |  | Medical, Nursing and Multi-Disciplinary Appraisal Process – Quality Indicator |  | X | X | X | X |
|  |  |  | Medical Job Planning Process – Quality Indicator |  |  | X |  | X |
| SR 2.5 | Established Directorate Financial Management Systems and Processes | National Director Health Protection and Screening Services, and Medical Director | Directorate Finance reports to Directorate Management Team meeting (monthly). Supported by the Business Operations Meeting (BOM) | x | x |  |  |  |
|  |  |  | Divisional Finance reports to SMT | X |  |  |  |  |
|  |  |  | Executive Director Reports (to Executive and Board) |  |  | X |  | X |
|  |  |  | Mid and End of Year Review Reports (Executive scrutiny) |  |  | X |  | X |
| SR 2.6 | Implementation of learning from incidents | National Director Health Protection and Screening Services and Medical Director | Datix reporting at programme and divisional level | X | X | X |  |  |
|  |  |  | Putting Things Right - Quarterly Alert Exception Report (Quality, Safety and Improvement Committee) |  |  |  | X |  |
|  |  |  | National Reportable Incident Reporting (Quarterly) to Quality, Safety and Improvement Committee |  |  | X | X |  |
| SR 2.7 | Surveillance of health threats to inform timely and effective response | National Director Health Protection and Screening Services and Medical Director | Communicable disease surveillance reports | X | X |  |  |  |
|  |  |  | Exceedance reports and protocols for escalation and response | X | X | X | X |  |
|  |  |  | Agreed criteria for escalation (reviewed on an annual basis) | X | X |  |  |  |
|  |  |  | Health Protection Situational Awareness Reports – (monthly report to Executive) | X | X | X |  | X |
| SR 2.8 | Development of Workforce Plans for each Division and established processes to enable effective Recruitment | National Director Health Protection and Screening Services and Medical Director | Reports of progress against developed Workforce Plans | X | X |  |  |  |
|  |  |  | Reports to the People and Organisational Development Committee |  |  |  | X |  |
|  |  |  | Directorate and Divisional-level workforce plans |  | X |  |  |  |

| Action Plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 2.1 | Divisional review of existing controls | MB | Work across Health Protection and Screening Services 3 service divisions to review existing controls and identify gaps, informing the developing action plan to be signed off at Directorate level | National Director Health Protection and Screening Services, and Medical Director | July 2022 | Complete – will continue to review |
| AP 2.2 | Integrated scrutiny and action planning at directorate level of available management information relating to finance, people, quality, and risk | MB | Review of current meeting cadence and information flows to identify gaps and opportunities | National Director Health Protection and Screening Services, and Medical Director | Complete | August update – Complete |
|  |  | MB | Strengthen existing system including reintroducing a directorate and business partner subgroup |  | Complete | August update – Complete |
| AP 2.3 | NHAIS is being decommissioned by England and we currently rely on NHAIS to select breast screening cohort. Reliant on one member of staff who has detailed knowledge of NHAIS. | SH | Implementation of BSS select for Breast Screening Programme to maintain cohort selection for breast screening. Working group with NHS England colleagues to progress this change | Deputy Chief Executive / Executive Director of Finance and Operations National Director Health Protection and Screening Services, and Medical Director | March 2023 | Feb 2023 – meeting in early Feb suggesting the plan lacked sufficient detail to provide assurances and very unlikely to produce any products this financial year. Decision taken to communicate with WG that unlikely to use capital funding identified this financial year. Meetings to include NHS E colleagues as well as NHS D to be more joined up and meetings held with NI who also going to use BS Select for cohort selection. Work will continue to progress. NHAIS is not being decommissioned in England until Dec 2024. Jan 23 update -Meetings have been established – both joint project team with NHS Digital and board meetings with NHS Digital and NHS England. Project outline received 31/01/23 from NHS D but there is uncertainty around timescales that NHS D are able to deliver to and the governance process timescales around the change. Queries have been shared with NHS D around granularity of how the system works to ensure processes can be adapted to deliver the solution for BTW. Meetings to be set up in Feb to discuss the detail. Timescales have low confidence to achieve. NHAIS is not being decommissioned in England until Dec 2024. |
| AP 2.4 | Recovery of the Breast Screening Programme is impacted by difficulty in recruiting specialist clinical staff to undertake reading of mammograms and assessment clinics. | SH | Recruitment processes underway for breast clinician role in North Wales. Planned recruitment in Southeast Wales for radiologist working closely with Health Boards. Planned retirement in 2023 will increase issue in North Wales and working with HB to explore potential ways forward. | National Director Health Protection and Screening Services, and Medical Director | March 2024 | Feb 2023 update as Jan with the additional note that we are progressing training option for breast clinician, but this will be medium term. All other actions progressing. Jan 23 update - Recruitment for breast clinician role in North Wales not successful as no suitable application. Exploring working with England to train breast clinician in North Wales on established training scheme. Exploring with HEIW to establish funding stream to training as potentially sustainable model and key across breast services in Wales. This will not support service in short term and still have considerable challenge when current radiologist retires. HB is out to advert for radiologist which if recruited will support BTW in North Wales but low confidence that will recruit. Planned recruitment in South East Wales progressing and expect improvement in substantive staffing levels from Spring 2023 which will support timeliness. |
| AP 2.5 | Sustainable provision of clinical infection services | RH/DH | Continue to recruit to consultant posts; Deliver changes that will make the service more attractive including recruitment of Specialty and Specialist Doctors as well as Physician Associates, Clinical Scientists and Specialist Nurses. | National Director Health Protection and Screening Services, and Medical Director | Ongoing | Remote consultant support is being trialled and has proven to be beneficial and extended to end of financial year. Service continues to search for additional workforce opportunities. |
|  |  |  | Proposal to convert non-pay Transformation funds to pay to increase number of clinical staff (Scientists and Specialist Nursing) |  | February 2023 Proposing May 2023 | Feb 23 – Feedback from DMT and DLT received for next iteration. The timeline needs to be extended by 3 months to allow for the necessary iterations and governance. Jan 23 – Draft shared and formal submission for February 2023 DMT |
| AP 2.6 | Sustainable provision of laboratory diagnostics including Out of Hours and workforce design | RH/DH | Review network model to optimise skill mix across multiple sites for Out of Hours working | National Director Health Protection and Screening Services, and Medical Director | February 2023 | Feb 23 - The review is complete. There is a work plan to ensure all staff can demonstrate and evidence competencies for OOH work. To be completed by September 2023 Jan 23 – Competencies agreed and signed off by SMT. Work plan to sign off all staff in development. |
|  |  |  | Complete training competencies for all staff who are able/required to deliver OOH services |  | September 2023 | Feb 23 - Recorded OOH competencies via iPassport for all staff required for OOH shift and on-call |
|  |  |  | Change skill mix to include greater numbers of Associate Practitioners (Band 4s) and reduce numbers of Biomedical Support Worker (Band 2/3) to secure higher-level competencies |  | March 2023 | Feb 23 - Complete Jan 2023 – To be closed as specific action completed. |
|  |  |  | Complete molecular testing tenders for provision of Respiratory and Central Nervous System syndromes to support workforce redesign. |  | March 2023 | Feb 23 – Centralised CNS procurement on schedule. New discrete action below for Syndromic molecular procurement Jan 23 – Following procurement advice, respiratory targets to be moved to the syndromic molecular testing tender. The centralised CNS tender is on schedule. |
|  |  |  | Complete Syndromic Molecular Procurement project to include: - Respiratory - GI - AMR - Bone and joints - BBV - Sexual Health |  | October 2023 | Feb 23 - Pre-Information notice issued and responses received from interested companies. Tender specification to be finished based on market dialogue. Procurement exercise will be based on syndromic lots and volume-based discounts. Funding routes are i. TAT and Resilience Business Case for agreed targets and volumes and ii. all else via Health Board SLAs. |
|  |  |  | Centralisation of Roche testing platforms at IP5 to provide i. centralised respiratory testing including COVID and ii. centralised sexual health infection testing including postal service. Enable redesign of virology / serology workforce |  | i. November 2022 ii. April 2023 | Feb 23 – RELOCATION & OPERATIONALISATION TO IP5 COMPLETED. Jan 23 – i. completed and ii. On schedule |
| AP 2.7 | Resilient Out of Hours Acute Health Protection Service | GS/ EM | Design, cost, procure and Implement new central contact process to support 24/7 operations | National Director Health Protection and Screening Services, and Medical Director | Completed | Complete – will continue to review |
|  |  |  | Reviewing the model of service delivery to test resilience and sustainability |  | March 2023 | Feb 23 – Consultation to end on 17 February 2023 noon. Feedback and comments to be reviewed subsequently and form part of the outcome report and recommendations Jan 23 – Formal consultation commenced on 10/01/2023. |
| AP 2.8 | Surge Plan for Acute Health Protection | GS/ EM | Agreed oversight and surge plan for Acute Health Protection | National Director Health Protection and Screening Services, and Medical Director | February 2023 | Feb 23 – discussions underway with EPBC team to further develop, align, and integrate Acute surge plan with the updated organisational Business continuity model and policy that is currently being updated. December 22 – completion date amended from Dec to Feb |

Risk Owner’s Overview Assessment Status

A number of functions play a material role in the effective management of change. People & OD have a key role, together with Strategy & Planning; in addition to the critical role of line managers in leading and handling change effectively. There are a large number of change programmes currently planned and already underway within the organisation. Although there are many measures already in place in relation to managing sickness, staff well-being, as well as the OCP process, it is recognised that until we move to a more controlled system for the commissioning and monitoring of change programmes, there will continue to be some risk that we will not be able to manage organisational change as well as we would like, due to over commitment.

| Risk 3 | There is a risk that we will not manage organisational change well, caused by multiple change programmes being implemented simultaneously, but in isolation, and insufficient time to effectively engage an exhausted workforce, resulting in high levels of sickness absence, vacancies, staff turnover and stress. |
| --- | --- |

| Sponsor and Assurance Group |  |
| --- | --- |
| Executive Sponsor | Director of People and Organisational Development |
| Assuring Group | People and Organisational Development Committee |

| Inherent Risk |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date | 28/02/2023 | Likelihood: | 5 | Impact: | 5 | Score: | 25 |

| Risk Score |  |  |  |  |  | Risk Decision | Delivery Confidence Assessment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Current Risk |  |  | Target risk |  |  | Treat | Amber |
| Likelihood | Impact | 15 | Likelihood | Impact | 9 |  |  |
| 3 | 5 |  | 3 | 3 |  |  |  |

| EXISTING CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 3.1 | Partnership working with Trade Union’s to engage at informal and formal stages of change and working with change leads to support initiatives | Director of People and Organisational Development | Appointment of 2 dedicated change Trade Union representatives to support change initiatives | X |  |  |  |  |
|  |  |  | Organisational Change Policy provides a framework to undertake change including staff engagement | X | X |  |  |  |
|  |  |  | Papers and Minutes to demonstrate the provision of updates to Local Partnership Forum, Joint Medical & Dental Negotiating Committee, Business Executive Team and People & Organisational Development Committee |  |  | X | X |  |
| SR 3.2 | Strategic Priorities in relation to planned change have been identified in the Integrated Medium-Term Plan (IMTP) | All Executive Directors | Papers and Minutes to demonstrate regular review via Project Boards to monitor progress and impact on workforce | X | X | X | X |  |
|  |  | Deputy Chief Executive and Director of Operations & Finance | Minutes of monthly meetings to review IMTP progress |  | X |  |  |  |
| SR 3.3 | A People & Organisational Development Organisational Change Policy change tracker in place to identify changes as they are initially discussed in order to identify planning and resourcing implications | Director of People and Organisational Development | Monthly meeting to demonstrate change initiatives discussed and monitored regularly with Partners and Trade Union Change Leads |  | X |  |  |  |
|  |  |  | Local Partnership Forum quarterly |  |  |  | X |  |
| SR 3.4 | Provision of change master classes to managers by external provider | All Executive Directors | Provision of change master classes to managers | X | X |  |  |  |
|  |  |  | Change toolkit available to support managers | X | X |  |  |  |
| SR 3.5 | Managing Attendance at Work proactively supported by People & Organisational Development Advisor team | All Executive Directors | Managing Attendance at Work Policy provides framework to support sickness absence management | X | X |  |  |  |
|  |  |  | Mandated manager training delivered locally | X | X |  |  |  |
|  |  |  | Directorate and Divisional Assurance Dashboards provide key insights to be acted upon by line managers with advice and support from People & Organisational Development. | X | X | X |  |  |
| SR 3.6 | Wellbeing provision in support of staff experiencing anxiety of change | Director of People and Organisational Development | Employee Assistance Programme | X | X |  |  |  |
|  |  |  | Occupational Health Provision | X | X |  |  |  |
|  |  |  | Minutes demonstrating directorate action plans monitored at Health & Safety Meetings | X | X |  |  |  |
|  |  |  | Staff wellbeing survey | X | X | X | X |  |

| Action Plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 3.1 | No clear picture or process of measuring / controlling the amount of change planned across the wider organisation and the impact this has for People &OD |  | Work being undertaken by Strategic Planning and Performance teams will allow greater understanding of planned changes and its impact | Deputy CEO and Director of Operations and Finance | Completed | September 2022 – Action completed |
|  |  |  | Oversight and informed decision making on proposed future change programmes | All Executive Directors | 30/06/2023 | Update 23/02/23 - A discussion paper aligned to the LTS and IMTP is being developed by Strategic Planning colleagues that will cover commissioning and resourcing processes to inform how as an organisation we intend to undertake change in the future. The due date for this action has been amended to reflect the associated work that will be required to enable informed decision making on future change initiatives as outlined in the IMTP Update 31/01/2023 - Further workshops for enablers to discuss the future scoping and commissioning of change programmes TBA by Strategic Planning, confirmed to be following the LTS refresh |
|  |  |  | Ensure the People & OD section of the IMTP fully reflects the change priorities for the period of the IMPT | Director of People and OD | 31/03/2023 | Update 28/02/23 - The IMTP has been reviewed to identify initiatives that have people implications as part of the enabler assessment and feedback provided for BET discussion regarding feasibility, scheduled for consideration today. Update 31/01/2023 – IMTP activity underway and on track Update 01/12/2022 -Workforce planning and IMTP activity currently underway in Directorates and on track |
| AP 3.2 | Expertise and understanding of how to lead change, whilst minimising the negative impact on staff |  | Development and delivery of a ‘Managing Change Effectively” programme, targeting People Managers to increase their capability in change management skills in support of organisational change | Director of People and OD | 31/03/2023 | Update 23/02/23 The future learning and development offer is currently being developed aligned to new resources that are being designed to support improving managers capability in leading change. A pilot and launch date are TBD as part of the new leadership and management development provision, scheduled for the new financial year. Update 31/01/23 Improving capability is part of the task and finish group activity that is on track Update 23/12/22 - Linked to IMTPM-317 and on track |
| AP 3.3 | Incomplete Directorate workforce plans |  | Develop and deliver training and support to build the skills of managers in planning, predicting and identifying workforce supply and demand. | Director of People and OD | Completed | Update 23/12/2022 - Linked to IMTPM_320. Initial sessions delivered to Directorate SMT’s by Strategic Workforce Planning and Resourcing Manager. All Directorates have now completed the first phase of workforce planning. |
|  |  |  | Integration of change management requirements in Directorate and Divisional Workforce Plans | All Executive Directors | 31/03/2023 | Update 28/02/23 Workforce requirements to support change are aligned to the update AP3.1 above Update 31/01/2023 –Directorate workforce information submitted and received and analysis being undertaken of these initial returns Update 23/12/2022 - Linked to above action as well as Long Term Strategy refresh and Quality as a Strategy work, which is on track. |
| AP 3.4 | Lack of agreed organisation design principles and process for commissioning and resourcing of organisational change work |  | Develop an agreed approach to organisation design, commissioning and resourcing of organisational change work for subsequent implementation | Director of People and OD | 30/09/2023 | Update 28/02/23 Following as assessment of the work required to enable appropriate commissioning, the deliverable has been agreed and moved to the new financial year. Update 31/01/2023 Outputs from both workshops being analysed and commissioning approach work is on track Update 23/12/2022 - The organisational design part of this deliverable has been agreed and moved into the new financial year, aligned to the LTS refresh. Update 01/12/2022 - First workshop held during November 2022 to co-create a common understanding & approach in POD to commissioning (internal and external), that will also support our planning and resourcing for initiatives as a Directorate going forward. Second workshop scheduled for January 2023. |
| AP 3.5 | Varied levels of staff engagement and involvement in change processes |  | Proactively involve staff in informal engagement and co-creation of change as an essential part of OCP activity for all new change initiatives | All Executive Directors | Ongoing | Update 28/02/23 The people aspects of change are being incorporated into the resources that are currently being developed in partnership with TU colleagues to support managers capability in leading change |
| AP 3.6 | Varied levels of engagement with TU colleagues at national level |  | Continue to strengthen relationships with national TUs to improve the culture of partnership working in PHW | Director of People and OD | Ongoing | Update 28/02/23 Work in progress through LPF and JMDNC |

Risk Owner’s Overview Assessment Status

The implementation of our People Strategy as well as our Strategic Equality Plan remain crucial to our ability to manage this strategic risk. With data insights taken from recruiting, leavers (exiting), movers (internal) and promotions, etc. there will be a continuous view of the current position. Our divisional / directorate workforce plans must be robust ensuring we understand our current talent, i.e. those in place to deliver now and what our future internal talent looks like. Where future talent does not exist within the organisation, there will need to be strategies to ensure gaps do not open up and leave the organisation vulnerable to failing to deliver.

| Risk 4 | There is a risk that we are unable to attract and retain the required professional workforce caused by skill shortages and increased pressures on staff, which has been exacerbated by the Covid-19 pandemic, resulting in there being insufficient capability and capacity to deliver our plans |
| --- | --- |

| Sponsor and Assurance Group |  |
| --- | --- |
| Executive Sponsor | Director of People and Organisational Development |
| Assuring Group | People and Organisational Development Committee |

| Inherent Risk |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date | 11/05/22 | Likelihood: | 5 | Impact: | 5 | Score: | 25 |

| Risk Score |  |  |  |  |  | Risk Decision | Delivery Confidence Assessment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Current Risk |  |  | Target risk |  |  | Treat | Amber |
| Likelihood | Impact | 15 | Likelihood | Impact | 9 |  |  |
| 3 | 5 |  | 3 | 3 |  |  |  |

| EXISTING CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 4.1 | People Strategy | Director of People and Organisational Development | Bi annual progress reports to BET and PODCOM |  |  | X | X |  |
| SR 4.2 | Directorate and Divisional Workforce Plans supported by P&OD BPs | All Executives | Workforce challenges and related workforce plans to address workforce issues are set out in IMTP narrative and workforce planning returns | X | X | X |  |  |
|  |  |  | Regular reporting and review, e.g. quarterly, is encouraged via Senior Management Team / Directorate Leadership Team / directorate performance reviews | X | X |  |  |  |
|  |  |  | Annual update via IMTP cycle |  |  | X | X |  |
| SR 4.3 | My Contribution/ Career development and Performance Check-ins | All Executives | Quarterly and monthly organisational and directorate level reporting and Performance Assurance Dashboard |  | X | X | X |  |
| SR 4.4 | Directorate and Divisional Assurance Dashboards providing key insights to be acted upon linked to workforce plans | All Executives | Directorate performance reviews | X | X |  |  |  |
|  |  |  | Active use of recruitment data | X | X |  |  |  |
|  |  |  | Analysis of Starter and Leaver data | X | X |  |  |  |

| Action Plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 4.1 | Develop robust workforce plans |  | Establish succession plans throughout the organisation for key roles | Director of People & OD | 30/12/2022 | Updated 1.3.23 A review of data submitted from directorates as part of the initial phase of workforce planning has been completed. A dashboard has been developed and will summarise where are our critical posts are. From this we will work with directorates to build succession plans for critical roles identified and identify key interventions required. (Data quality needs further attention) 24/1/23 The update remains the same as last month Updated 1/12/22 The update remains the same as last month Updated 17/11/2022 - Whilst this objective will not be met by the 30/12/2020 as part of the workforce planning process, key roles for succession planning will be identified by mid Q4. By the end of Q4 we will be developing targeted interventions from the analysed data to ensure robust succession plans are in place for critical roles. |
|  |  |  | Establish more detail of the workforce required to deliver our refreshed long-term strategic plan, including role mix, grade mix, skill mix, and placement of roles in the wider Public Health system | Director of People & OD | 30/12/2022 | 1 Updated 1/3/23 Baseline data to support this action has now been established. The data is currently being reviewed with Directorates and skill /role mix requirement will continue to be considered in line with LTS which is yet to be finalised. 21/1/23 The update remains the same as last month Updated 1/12/22 Data is currently being gathered as part of the Workforce Planning exercise and the LTS is moving closer to being finalised. Updated 17/11/2022 with the refreshed LTS not yet complete, an element of this risk will continue. |
|  |  |  | Develop clear plans for addressing scarce and emerging skills in line with local and national shortage specialities and forecast gaps between skills supply and demand | Director of People & OD | 31/03/2023 | 1/3/22 Updated 1/3/23 This is ongoing as part of the workforce planning discussions being help with Directorates. 21/1/23 The update remains the same as last month Updated 1/12/22 The update remains the same as last month Updated 17/11/2022 By the end of Q4 plans will have commenced with directorates as part of the current approach to WFP to discuss how each will develop interventions from the analysed data and then develop plans to meet the supply issues |
|  |  |  | Work with our partners to raise awareness of and widen access to careers in Public Health, e.g. through advanced apprenticeships or other non-graduate routes (to expand our supply of suitably experienced candidates and increase participation and progression from under-represented groups). | Director of People & OD | 31/03/2023 | 1/ Updated 1/3/23 February BET cancelled the paper will now go on the 7th of March 21/1/23 A paper will be presented to BET on the 20th Feb to seek provision of funding to support entry level roles which support longer term succession planning Updated 1/12/22 - Work continues in line with November update Updated 17/11/2022 work will continue, but the approach will fall out from the workforce planning work as opposed to being achieved in isolation |
|  |  |  | Increase the number of placements, secondments, honorary contracts and joint posts spanning organisation boundaries, increasing skills transfer in both directions | Director of People & OD | 31/03/2022 | Updated 1/3/23 Remains unchanged 21/1/23 This needs to be targeted and will be shaped by information provided via the workforce planning process. Updated 1/12/22 - As Above Updated 17/11/2022 - As above |
| AP 4.2 | Ensure PHW’s employment offer helps retain top performers and attract the best external talent. |  | Develop a compelling employee value proposition and employer brand for social media and recruitment advertising whilst ensuring the lived experience matches the promise. | Director of People & OD | 31/03/2023 | Updated Updated 1/3/23 Joint Leadership and Exec Team workshop held and feedback from data gathering phase shared. Project delivery is on plan. 21/1/23 Project aims and objectives presented to PODCOM in Jan 23. Positive feedback received. Focus group sessions taking place throughout January. Plan is on track. Updated 1/12/22 High level of engagement achieved with key stakeholders. The project is on plan and progressing well. Updated 17/11/2022 the project has commenced |

Risk Owner’s Overview Assessment Status

Successful delivery against the objective appears feasible, however, there are significant dependencies/actions, including: - recruitment and onboarding of key hires, which have now been completed. These hires are now in post and embedding to PHW. - acquiring of new skills and ways of working, - building of relationships to establish robust and ongoing collaboration within the directorate, across the organisation and wider partners to ensure we maximise the benefit across all data sources including surveillance, screening, non-communicable disease and wider determinants of health. - Establishment of the Business Design Authority with delegate responsibility being fully operational. - The discovery phases have highlighted numerous areas for improvement and so funding to take the various discovery phases through into alpha/beta and live has become increasingly important. We will continue to develop actions based on user insights and engagement.

| Risk 5 | There is a risk that we will fail to exploit data to inform and direct public health action and interventions. This will be caused by data being held in silos, difficulty accessing the data and inability to access to provide the impact on public health. This will result in worse public health outcomes in Wales and increased information governance risk within Public Health Wales. |
| --- | --- |

| Sponsor and Assurance Group |  |
| --- | --- |
| Executive Sponsor | Executive National Director of Data, Knowledge and Research |
| Assuring Group | Knowledge, Research and Information Committee |

| Inherent Risk |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Date | 25/11/2021 | Likelihood: | 5 | Impact: | 4 | Score: | 20 |

| Risk Score |  |  |  |  |  | Risk Decision | Delivery Confidence Assessment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Current Risk |  |  | Target risk |  |  | Treat | Amber |
| Likelihood | Impact | 20 | Likelihood | Impact | 12 |  |  |
| 5 | 4 |  | 3 | 4 |  |  |  |

| KEY CONTROLS |  |  | SOURCES OF ASSURANCE | Level at which the Assurance is provided to |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | Control | Exec Owner |  | Team / Division / Project /Programme | Directorate Team / Exec Lead | Business Exec Team / Sub Groups | Committee / Sub group | Board |
| SR 5.1 | Development of research & evaluation and digital & data strategies for Public Health Wales to take drive forward our needs on this area. | Director of Data, Knowledge and Research | KRIC on behalf of the Board |  |  | × | × | × |
| SR 5.2 | Developing our data storage, access and linking as part of the Local Data Resource and contributing/interacting with DHCW for other data needs in Health Care. | Director of Data, Knowledge and Research | Internal audit in Q4 | × | × |  |  |  |
| SR 5.3 | Recruitment into new investment posts progressing quickly to bring in additional skills | Director of Data, Knowledge and Research | Management control | × | × | × |  |  |
| SR 5.4 | Ensure we maximise exploitation of our data and information | Director of Data, Knowledge and Research | KRIC on behalf of the Board | × | × | × | × | × |

| Action Plan No. | Gaps in controls |  | Action Plan | Exec Director | Due Date | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| AP 5.1 | Data standards and validation |  | To have all our data accessible through one place | Director of Data, Knowledge and Research | 31/03/2023 | January 2023 Alpha phase for DESW commenced. January 2023 Discovery phase for our web estate commenced. February 2023 Discovery phase for screening IT systems. February 2023 Digital & Data Strategy now in Draft for submission to Business Design Authority and then KRIC in March 2023. |
| AP 5.2 | Lack of near real-time data to support decision-making |  | Develop a Public Health overview dashboard | Director of Data, Knowledge and Research | Complete |  |
| AP 5.3 | Lack of appropriate skills to meet the challenges we face |  | Recruitment of key personal to fill gaps in skills and knowledge | Director of Data, Knowledge and Research | Complete |  |
| AP 5.4 | Strategic framework to progress |  | Develop and agree a research and evaluation strategy and a digital and data strategy | Director of Data, Knowledge and Research | Complete |  |
| AP 5.5 | Not developing appropriate user-focused solutions |  | Move from discovery phase into alpha phase for diabetic eye screening and begin to implement service improvements | Director of Data, Knowledge and Research | Complete |  |
| AP 5.6 | Lack of comprehensive over-arching evidence base/understanding of user-needs |  | Undertake a discovery phase into a single register of non-communicable and communicable diseases | Director of Data, Knowledge and Research | 31/03/2023 | January 2023 - Discovery phase on a single disease registry commenced. |
| AP 5.7 | Assurance for maximising exploitation of our data and information |  | Develop research and evaluation strategy and Digital and Data strategy in support of the long-term strategy | Director of Data, Knowledge and Research | 28/02/2023 | 21.12.22 Research & evaluation strategy high-level principles agreed and digital and data strategy work commenced. These will be completed to support long-term strategy |
|  |  |  | Five data sciences projects to be agreed | Director of Data, Knowledge and Research | 31/03/2023 | 21.12.22 Delayed due to new hires not in post. Date moved. |