# Service Review

Adapted from ‘Methodology for Conducting a Service Review/Design’, PHW 2010

| Before starting |  |
| --- | --- |
| Project proposal | Project lead should write a proposal which sets out the aims and objectives of the service. |
| Identify project manager | - The manager is responsible for progression of the review on a day-to-day basis, and reports to the project lead. - The manager will ensure the project follows the agreed plan and timetable. |
| Agree Terms of Reference | - What is in and out of scope for this review? - Agree a project plan and timetable. - Is this review to describe performance of the service or to offer recommendations for improvement? |
| Working group | - The membership of the working group will be dictated by the exact nature of your review. - Consider if any external expertise is required eg PHW. |
| Assess the needs of the service | - Consider a systematic approach eg Health Needs Assessment [link] - Use of routinely reported data (appendix 2). |
| Literature review | - Identify recommended models of care, the evidence base for the service, good practice guidelines, and views of service-based professionals. - eLibrary for Wales - link - Consider use of your organisation’s library service |
| Assess current service provision |  |
| Describe service | - Describe the service in terms of quantity, distribution, and quality. - Consider elements of the Duty of Quality - link - May include: - Activity data - Waiting list data - Staffing data - Costs - Views of service users |
| Analyse performance | - Compare the service against guidance / recommended models of care as identified by the literature search. |
| Recommendations for changes (if included in this review) |  |
| Considerations | - Need for a phased approach – short, medium, long term - Costs involved - Timescales - Effects of change on workforce (change management) - Effects of change on service users, particularly those with protected characteristics (conduct equality impact assessment) |
| Report, Quality Assurance & Stakeholder Engagement |  |
| Report | - A report should be drafted and submitted. (See document template) - The report may be a description of the service or include recommendations, as agreed in the Terms of Reference. - The draft report should be quality assessed by the Project Lead. Advice may be sought from PHW. - Obtain feedback from stakeholders and amend as appropriate. |
| Post-study |  |
| Circulation | - The report must be circulated to those who will be affected by its findings, including the Board of Directors, the Executive Team, and other relevant stakeholders. |
| Review and evaluation | - A review of the project should be conducted after its completion. This includes a review of the processes and methodology against the Terms of Reference in order to identify successes, problems, and gaps. - The review may be written up as a ‘lessons learnt’ report. |
| Feedback | - Wherever possible, feedback should be obtained from the requesting body to state how the service review has been used and to state if it fulfilled its requirements. |

# Appendices

## Appendix 1 – Key steps for a service review

Project Proposal Form Written

Stakeholder consultation

Stakeholder consultation

Source: Methodology for Conducting a Service Review / Design, PHW 2010

## Appendix 2 – Routine data sources

- Census, ONS - link

- Population estimates and projections, ONS - link

- Child measurement programme Wales (CMP)

- Hospital activity data – Health Board own data, Stats Wales, Digital Health and Care Wales

- Survey data = National Survey for Wales, Health Behaviour in School-aged Children Study (HBSC),

## Appendix 3 – Report template

Service review/ redesign report template

1.	Executive summary

2.	Definition and scope of the service review/ design

- Purpose of the document i.e. background to the study, its aims and objectives, a broad description of what is being reviewed.

- How and why this service needs to be designed/redesigned.

- If there are any concerns about the quality or capacity of a service, what evidence is there regarding the extent of the issue.

3.	Needs assessment

- State whose needs are being addressed (geographical area, client group etc.).

- Outline the size of the need i.e. numbers in the population / client group.  Include trends and projections.

- Outline the extent of the problems (i.e. the “burden of disease”), in terms of morbidity / disability.

- Provide comparative data, e.g. local authority, regional, national, European.

- Describe gaps in the data, and if there was a need to extrapolate.

- Describe any caveats with the data.

4.	Service profile

- Describe the structure of the service - if any - currently being received, including the patient pathway where applicable.

- Present activity (e.g. patient numbers and bed use) and waiting list statistics.

- Present staffing complement and vacancies data.

5.	Service model /option appraisal

- Describe the recommended provision or “best practice” for this service.

- Describe any shortfall in the provision, including any inequalities.

- Describe the implications of any gaps in the provision.

- Describe the option(s) for a new service model.

6.	Conclusion and summary

7.	Recommendations

8.	References

9.	Appendices

- List of figures and tables

- Task and Finish Group membership and acknowledgements

- Methodology including any collaborative working

- Data sources

- Supporting / extra data