## Cluster plan
Activity/ project title | New or existing activity | Brief activity/ project description | Results/ benefits expected by end March 2024 | Strategic alignment: Ministerial priorities | Strategic alignment: RPB Area Plan | Strategic alignment: SPPC key programme priorities | Activity/ project budget (enter number only) | Funding source(s) | Current status | Comments | What has gone well since April 2022? | What has gone less well since April 2022? | Are there any particular challenges or issues the cluster would flag to the LHB, SPPC or Welsh Government?
Cluster Pharmacy Team | Existing (ongoing from 2021-22 plan) | Expand provision of the Cluster Pharmacy Team | Enables GP to focus on GP time to spend on patients with complex medical needs. Annual medication reviews carried out in a timely manner. | None | None |  | 130000 | Cluster funding | Started but delayed or paused | Availability of band 7 pharmacists is an identified constraint | We have continued to work closely with our district nursing teams, social and care workers, and our third sector partners, communicating remotely where necessary. | Waiting times for secondary care have been a serious concern during the pandemic. | There is a lack of clarity for practices on the contractual and financial mechanisms to carry out enhanced services for neighbouring practices of clusters
Cluster Pharmacy Team | Existing (pre-dates 2021-22 plan) | Cluster Pharmacy Team consisting of 2 Pharmacists (1.6 WTE) and a Pharmacy Technician (0.8 WTE, in post since December 2022) | Diversification of the workforce ensures patients are able to see the most appropriate professional in a timely manner. Enables GP to focus on GP time to spend on patients with complex medical needs. DOAC, new and annual care home medication reviews carried out in a timely manner as well as a range of other medication reviews being delivered. Pharmacy Technician to support and enable expansion of workstreams in line with prudent healthcare principles | Supporting the health and care workforce | Community Infrastructure | Community Infrastructure | 160000 | Cluster funding | Started & on track | Original Pharmacy Tech in post from November 2020 to August 2022. New Pharmacy Tech recruited, commenced post in December 2022 Expansion of Cluster Pharmacy Team allows additional support to be given to the emerging workload and prescribing cost pressures seen in Primary Care. | Previous pharmacy technician set up My Health-on-line for care home medication ordering on-line, ease of burden on practice staff and allows audit trail. Pharmacist carrying out DOAC reviews alongisde care home work, QAIF work and general tasks. Evaluation and reporting of QAIF AF project and patient safety dashboard by Pharmacists have provided continuity, allowed for comparison and sharing of good practice across all 3 practices. | Increasing workload pressure. QAIF: Welsh NHS delays in clarification, criteria setting, late proformas resulting in extra time demands in the report and evaluation process. Excessive medicines shortages and lack of continuity of Community Pharmacy staff resultant in extra workload for GP Practices and Cluster pharmacy team. Secondary Care Mental Health Service lack of staff continuity/staffing problems resultant in liaison breakdown with GP Practices and Cluster Pharmacy Team with regard to lithium shared care, antipsychotic annual statements. Ongoing District Nursing Service recruitment and retention problems resultant in delays in obtaining blood results, blood pressure values, consequence for planning and completing DOAC reviews and other medication reviews. | Delays in forwarding Health Board necessary templates, criteria and/or guidance in respect of Contractual/QI work . The Cluster Pharmacy Team project is well establlished and a highly regarded service. Until this project becomes mainstreamed, the majority of Cluster funds is committed to this workforce which restricts the Cluster in investing in new innovative projects.
Chronic Conditions Nurse (0.60 WTE) | Existing (pre-dates 2021-22 plan) | Recruitment of a CCM Nurse who commenced in post June 2022. The aim of the CCM Nurse is to support the review and management of housebound patients with chronic conditions, including patient education to create resilience. GP Practices within the West directly refer those patients who suffer from chronic respiratory disease, heart disease and/or diabetes mellitus who are either housebound or resident in a care home to the Nurse. | Improve the quality, consistency of care for these patients and to reduce potential hospital admissions with an additional focus on prevention to support with the proactive management of patients with chronic diseases. | Supporting the health and care workforce | Community Infrastructure | Community Infrastructure | 32000 | Cluster funding | Started & on track | Cluster successfully recruited to the post in June 2022 | Since being in post the CCM Nurse has been working closely with the 3 GP Practices within the Cluster to establish good working relationships. The Nurse also works closely with the Integrated Health and Social Care team which enables her to have direct access to therapists within the MDT, including members of the third sector. Following assessment of the patient and carers needs, referrals to such specialist therapists can be instigated; providing wrap around care alongside ongoing support where needed. | Taken nearly a year to recruit to the post. This was due to the pandemic and the lengthy Health Board recruitment process. Therefore the GP Practices have been managing this cohort of patients while recruitment has taken place. | Lengthy recruitment process. The Cluster has continually invested in the post of a CCM Nurse as a project as they feel the role is key in treating and managing their housebound patients with long term chronic conditions. For noting: Bridgend West has a higher percentage of older peope living with moderate/severe frailty than the CTM Health Board average. Dementia prevalance is also high in this area, 1.0%, the highers of all the Clusters within CTM The project has proven to be successful with both Bridgend East and Bridgend North investing in CCM Nurses. As a result the Cluster would like to see this project mainstreamed.
Valleys Steps - Children & Young People Resilience Project | Existing (ongoing from 2021-22 plan) | Working with Valleys Steps the Cluster is delivering a resilience, stress control and mindfulness programme to pupils of Year 10 at both local comprehensive schools. Following the pandemic and the return of children/young people to schools, teachers have seen a rise in students presenting with a variety of emotional/mental health issues. | The aim of the resilience and stress control/mindfulness programmes is to improve the knowledge and understanding of children and young people to the effects of stress and anxiety. Learning about resilience and mindfulness and how they all play a part in reducing anxiety and to help improve overall wellbeing. | Mental health and emotional well-being | Mental Wellbeing | Mental Wellbeing | 15500 | Cluster funding | Started & on track | This project has more or less taken 16 months to progress due to the ‘stop start’ effect of the coronavirus pandemic. | Feedback from pupils is very positive. Following the courses the majority of pupils have felt better able to manage stress, more able to solve problems, and that their overall wellbeing haa improved. When asked what was the most useful thing that they learnt, students identified some of the breathing exercises, ways to deal with stress and anger, and self-care. The Cluster are now delivering these sessions to both Comprehensive Schools within the Cluster footprint. Additional support for GP Practices and local comprehensive schools is crucial as both are reporting a rise in students presenting with a vareity of emotional and mental health issues | Time taken to deliver these classes. Continued meetings needed with both local comprehensive schools to progress this project. | Mental health and anxiety being experienced by children and young adults. Access to local CAHMS service - long waiting times. Comprehensive schools have counselling/student support facilities however the waiting lists can sometimes be long. Therefore the schools are grateful for the additional support the Cluster has provided to help with the levels of anxiety being experienced by many of their pupils.
First Contact Practice Physiotherapy | Existing (ongoing from 2021-22 plan) | CTMUHB Physiotherapy services to deliver first contact physiotherapy services to Clusters as part of the planned care recovery programme. | Benefits have consistently been identified for both Primary Care (supporting sustainable GP workloads) and Secondary care (reducing referrals to Orthopaedics, radiology and interface services (MCAS). The FCP Physiotherapy model delivers on national and local policy drivers. It provides a prudent partnership-working model to increase GP capacity and address sustainability and delivers across the quadruple aims identified in a Healthier Wales. Effective management of patients within primary care without the need to refer onto secondary care. | Supporting the health and care workforce | Community Infrastructure | Community Infrastructure | 8600 | Cluster funding | Started & on track | FCP started in West Cluster on 1st August 2022. | Few teething problems with the start-up of the service, these have now been resolved. Quarterly stats shared with the Cluster. Established a very good working relationship with the Physio team. | Estate issues with 2 of the 3 Practices within the Cluster, lack of space. North Cornelly is hosting Heathbridge patients until Heathbridge Improvement grant work has been completed. Patient's not willing to see a physio insisting on seeing the GP, work ongoing to try and educate patients. Uncertainity of future funding from Health Board recovery monies to sustain services. Cluster monies are limited. 7 sessions allocated to the Cluster in the original agreement, however only 6 sessions are being delivered due to capacity within the FCP service. | First contact physiotherapy service has been funded to date via planned care investment. However, funding has yet to be agreed for 23-24. The cost could potentially come out of the Cluster budget for 23-24 which is approximately £9,000.00. Uncertainty of future funding and the use of Cluster funds to support this project. Until this becomes mainstreamed Cluster funding for new projects is limited.
Vision Support Software | Existing (ongoing from 2021-22 plan) | Investment in Vision 360 software to support the First Contact Physiotherapy service | Continued use of software package by Practices to book appointmemts directly to this service. | Supporting the health and care workforce | Community Infrastructure | Community Infrastructure | 3500 | Cluster funding | Started & on track | To have this centrally funded would be a benefit | System is being used by all 3 Practices | One of the Cluster Practices has taken the role of 'lead admin' to ensure the diaries of the physio's are up to date and clinics organised. The Cluster is renumerating the Practice for this additional work and responsibility. | Additional administration time and responsibility taken by a lead Practice in order for the clinics to be effective. This was not a role anticipated by the Practices when the project was rolled out.
Mental Health Project | New (2022-23 plan) | GP Practices offer the frontline service for patients suffering with mental health issues. Such issues have become increasingly prevalent, particularly due to reduction in stigma associated with mental health and the impact of Covid so it’s crucial that Practices are more equipped to offer the best possible service and care to patients. Following an audit carried out by one of the Cluster GP Practices in respect of their patients suffering with mental health this Practice is trailling a dedicated face to face weekly mental health clinic, the aim of which is to try and reduce emergency crisis calls. | GP Practice is updating the Cluster as to the effectiveness of its dedicated mental health clinic, sharing lessons learnt. The Practice also aim to work with both BAVO and Integrated Team who can possibly offer these patients additional supportwith their unmet needs. | Mental health and emotional well-being | Mental Wellbeing | Mental Wellbeing | 0 | Cluster funding | Started & on track | Funding provided by the Cluster for GP protected time to carry out the original audit. | Practice are running a dedicated clinic, once a week for patients who request appointments for a mental health complaint. At first contact with a patient stating ‘it’s urgent’ they will be asked if their preference of a consultation in the Practice dedicated mental health clinic, with its benefits of longer consultations and pre-arranged follow up, or an urgent appointment for the on-call doctor. If the patient feels it is urgent for that day, the on-call Doctor will still be in touch. The doctor can then themselves triage the presentation and if appropriate defer them to the weekly mental health clinic. Initially, the clinic with will comprise of 8 x 15 – 20 minute pre-bookable, morning appointments which can be telephone or face to face depending on the patient’s preference. Following this, there will be 4-6 x 10 minute follow up appointment to review patients from a previous mental health clinic | Delays to project due to locum availability | Clarity on mental health services available to patients and referral options for GPs.
AWDPP | New (2022-23 plan) | Public Health Wales are leading the development and implementation of an All Wales Diabetes Prevention Programme with plans to roll it out across Wales over the next 3 years. They plan to start initial roll out in March 2022, two clusters per health board have been recurited for this first wave of implementation. Merthyr and the West Cluster have been chosen for CTM UHB | •Patients identified on GP system with HbA1c 42-47mmol/mol and aged 18 years and over on VISION or EMIS - Standardised invitation letter will letter will invite patients to book an AWDPP appointment and contain localised booking information - If the patient does not respond to the AWDPP invitation letter, a follow up phone call should be made by the HCSW in an attempt to enhance patient engagement with the intervention. A phone call script has been developed with behavioural science input will be provided for use | Population health | Community Infrastructure | Community Infrastructure | 0 | Other specified source | Started & on track |  | From October 2022 - February 2023 AWDPP stats are as follows: - People id using AWDPP search template 288 - Invitations sent to attend the AWDPP (following manual exclusion) 244 - AWDPP consultants booked 124 - AWDPP consultations completed 85 - DNA 6 (7%) - 28 referred to weight management scheme - 27 referred to physical activity - 4 referred to other support services (help me quit) | Delays to the project due to issues around joint controller agreement. These have now been resolved. GP Premises issues. Space is at capacity in two of the 3 GP Surgeries therefore these sessions are being run from North Cornelly Community Clinic and Pyle Life Centre.
Accelerated Cluster Development (ACD) Programme | Existing (ongoing from 2021-22 plan) | In 2022 the Strategic Programme for Primary Care introduced the Accelerated Cluster Development (ACD) Programme. This has meant a change to the GP Cluster domain within QIF. The ACD programme proposes the development of Professional Collaboratives (PCs) for each of the independent contractor groups. A lead from each collaborative will engage and work with other collaborative leads to form the core membership of the cluster. | The cluster is committed to engaging in the ACD model. GP Collaborative for the West has been formed with meetings scheduled for 6 times a year. Terms of Reference have also been agreed. | Population health | Community Infrastructure | Community Infrastructure | 0 |  | Started & on track | West Cluster meetings have been split into two parts. GP Collaborative meet first followed by the Cluster meeting. | During the foundation year the speed at which the GP Collaborative was set up. Sharing of the Population Needs Assessment by Public Health. Terms of Reference of GP Collaborative agreed. ACD Programme Manager recruited | As at July 2023 only two other collaboratives have been set up and joined the Cluster meeting - Community Pharmacy and Allied Health Professionals. Frustration at the delay of Dental and Optometry Representatives joining the Cluster Planning Group. | Delay/timeliness in set up of Dental and Optometry Collaboratives.
Population Segmentation | Existing (ongoing from 2021-22 plan) | Cluster and individual Practices are commited to work with PHW collegues in order to get a better understanding of population health. identifying the areas of need and exploring how these needs can be met in collaboration with other partners. | The intelligence will enable services and interventions that are already in place to be targeted to individuals according to, not only their current, but future need making their prevention capacity more effective and efficient. More timely, targeted upstream prevention intervention will increase effectiveness and efficiency leading to improved patient outcomes. Where gaps exist, new interventions can be identified from the published evidence with support from Public Health. | Population health | Community Infrastructure | Community Infrastructure | 0 |  | Started & on track |  | Population Health and Risk Stratification Data available to Practices via the Primary Care Information Portal. Local Public Health Rep for the West with a member of staff from the West Integrated Team carried out a ‘backwards’ look at data, reviewing those citizens that have already been referred to an MDT and matched this information to the Primary Care Information Portal to identify their associated segments and risk score. This approach places minimal resource requirement on the Primary Care General Practice settings given the care the patient needs has already been identified and the referral to the appropriate intervention has taken place. | Time needed by GP Practices to carry out the data analysis of segmentation data. Inability of Cluster Development Managers to access this data. Access will enable the CDM's to assist and support Practices with reviewing their segmentation data. | Cluster Development Managers unable to access the population health and risk stratificaiton data due to Data Protection issues.
Bridgend West
HELP: Follow the numbers; click on a cell in the header row for instructions; see 1st row example.
1
Listing activity/ projects: List activities or projects planned to commence during 2023-24, as well as those planned/ initiated in 2022-223(or earlier, if ongoing).
2
3
Looking back: Brief reflections on delivering the 2023-2024 cluster plan.
4
Looking forward: Potential challenges in delivering the 2023-2024 cluster plan.
Bridgend
Cluster
PCPG