Accessible Information Standard

Final Project Report

1. 	Background

The All Wales Standards for Accessible Communication and Information for People with Sensory Loss were launched in December 2013 by the Minister for Health and Social Services, Mark Drakeford AM.   The Standards set out the level of service delivery that people with sensory loss should expect to be met whenever they need healthcare.

The Standards also require every Health Board and NHS Trust in Wales to develop an implementation plan that is led by a designated senior officer and sets out clear timescales and actions for delivery. Progress on the delivery of the plan should be monitored regularly and reported formally to the Board.

The All Wales Standards were developed as a result of the ‘Accessible Healthcare for People with Sensory Loss in Wales’ report which required all healthcare organisations to have an ‘...Accessible Information Policy outlining how the communication needs of all patients are to be met, including the needs of people with sensory loss...’.

The Centre for Equality and Human Rights (CEHR) worked closely with Welsh Government, Action on Hearing Loss Cymru and RNIB Cymru as well as other sensory loss organisations and people with sensory loss to develop the All Wales Standards.

2. 	Accessible Information Standard

As a direct result of the ‘All Wales Standards’, it was clear that what was needed was an Accessible Information Standard, (‘The Standard’).  The Standard is a national project led by Welsh Government in partnership with the Centre for Equality and Human Rights (part of Public Health Wales), health boards, NHS trusts, NHS Wales Informatics Service (NWIS) and third sector partners. The Standard requires GP surgeries to capture, record, flag and share the communication and information needs of patients with sensory loss.

It is a tool and enabler to help health boards meet their legal duty under the Equality Act 2010 to make reasonable adjustments for disabled patients and the public.  It also ensures that the communication and information needs of those with sensory loss are captured and shared consistently across all health boards and NHS trusts.

The Project had 2 phases:

Phase 1 – capture and record the communication and/or information needs of patients who have sensory loss within the GP information systems.

Phase 2 – include the recorded communication and/or information needs in all e-referrals, not just to audiology and ophthalmology but to all areas

Very little information of this kind had been routinely captured and recorded in GP surgeries and hospital departments. This meant that it could be difficult for information about a patient’s communication needs to be safely and effectively shared within and between GP surgeries, hospital departments and other healthcare services.

Since November 2017, GP surgeries have had the functionality to identify and record the information and communication needs of their patients with sensory loss. The system also provides tools for GP surgery staff on how to meet a patient’s needs once identified, such as how to generate letters in large print and how to add prompts to a patient’s medical record.  Over the last year, additional work has been taking place on phase 2 to add further functionality.

This additional functionality will ensure that when a GP surgery makes a referral to hospital services, a patient’s information and communication needs will be automatically sent with the referral.   This work is expected to be completed by December 2018.

3. 	Engagement with the Community and Health Professionals

It was identified early on in the project that IT functionality was only ever going to be a small part of ensuring its success.  The success of The Standard will largely rely on the awareness of GP surgeries of their responsibility to capture and record this information, and the willingness of patients to share their communications and/or information needs.

It has to be a two-way process if it is to be a success for both general practices and the sensory loss community. Alongside a mandate from Welsh Government, there was a need for extensive engagement with both health professionals and the sensory loss community to explain the purpose of The Standard and to encourage and support GP surgeries and the sensory loss community to share and capture communication needs.

3.1 	Community Engagement

Engagement began in October 2017 with visits to audiology and ophthalmology outpatient departments.  The Standard was the central theme of the ‘It Makes Sense – Sensory Loss Awareness’ Campaign run by NHS Wales throughout the month of November 2017 and the following key campagin messages for patients and the public were shared to support the new Standard:

TELL doctors, nurses, paramedics and other health professionals how you want staff to communicate with you;

ASK to receive information in an accessible format including British Sign Language (BSL), large print, audio, electronic or Braille;

SHARE your concerns with your GP surgery or hospital if the information you receive is not accessible to you.

Between November 2017 and February 2018 a great deal of engagement  took place with Deaf Clubs around Wales, with Michelle Fowler-Powe on secondment to the CEHR from the British Deaf Association (BDA) and Claire Sullivan from the CEHR team presenting to Deaf Clubs in Cardiff, Newport, Pontypridd, Swansea, Bridgend, Neath Port Talbot, Ebbw Vale, Narbeth, Conwy, Mold and Wrexham.

From January 2018 Marcia Morgan, Welsh Government, was seconded to the CEHR to lead on a programme of further engagement with both the community and health professionals to raise awareness as well as asking for ideas to develop resources to help both the community and health professionals capture and record the communication and information needs of those with sensory loss.

Between January and September 2018 presentations were made to a number of local community groups organised by Action on Hearing Loss, Cyrmu, RNIB Cymru, Wales Council for Deaf People, Wales Council of the Blind, Sight Cymru, RNIB Cymru and Deafblind Cymru.  During the entire period of community engagement, nearly 600 (588) members of the Sensory Loss Community were involved.

3.2 	Engagement Feedback

The groups were asked about what would help to enable them to effectively communicate with staff in their GP surgeries.  Groups included those who are Deaf and use British Sign Language as their first language, deaf, hard of hearing, blind, partially sighted and those with dual sensory loss.

The sensory loss community is very diverse. Many of the communication barriers and challenges for those who are blind or partially sighted are similar to those who are D/deaf or hard of hearing but the solutions may be very different. For those with dual sensory loss, the solutions can be more challenging because of the loss of both hearing and sight.

The main themes from engagement are summarised in Appendix 1.

3.4	Health Professionals and Primary Care Engagement

Engagement with health professionals and colleagues in primary care teams began with the Eye Care conference held in September 2017 followed by the National Primary Care conference in November 2017.   Through the support of colleagues on the all Wales group, the majority of engagement was undertaken through presentations to cluster group meetings primarily in Cardiff, Bridgend, Neath Port Talbot, Merthyr, Monmouthsire, Mid Powys, Carmarthen, North Denbighshire and Wrexham. Where the CEHR was unable to secure a physical slot at a meeting, a written briefing note was provided.

3.5	Engagement Feedback

Overall, the feedback from cluster groups was positive with lots of ideas shared about how the resources being developed might help surgeries.

Practice Managers liked the idea of a form to hand in to the receptionist which admin staff could use to input the data.Some practices also felt it would be useful if the patient had a card stating their communication and/or information needs. Several have been developed by a number of public and third sector organisations in England and Wales.

There were three key messages shared with health professionals to help ensure the success of The Standard and taken from the ‘It Makes Sense’ campaign:

Find Out from the Sensory Loss e-learning module the most effective ways to communicate with people who are blind or have sight loss, who are deaf or hard of hearing or are deaf blind.

Ask patients how they would like to communicate with you.

Offer to give the information in an accessible format, including BSL, large print, audio, electronic or Braille.

4.	Resources

The CEHR commissioned the Centre of Sign, Sight and Sound (COS) to develop a range of resources to support general practices to implement the Standard.  Posters, leaflets and screenshots for TV monitors have been produced in white and yellow backgrounds.

A QR code link to a BSL version of the leaflet has been included to ensure the information is accessible to the Deaf community.  Additionally a BSL video of the poster and screenshot which includes audio and subtitles has been produced as a helpful addition to increase the ease with which people can recognise the choices being offered.

A BSL video resource for reception staff will shortly be available to all NHS Wales staff.  The video is intended to support reception staff to meet and greet Deaf patients and was developed with support from a general practice in Cardiff and Vale UHB and Accident and Emergency staff in Cwm Taf UHB.

A suite of e-learning modules have been developed to complement the statutory equality training for the NHS Wales workforce called, ‘Treat Me Fairly’. These include a sensory loss e-learning module developed in collaboration with Action on Hearking Loss, Cymru and RNIB Cymru.

A communication plan to raise awareness and share the resources through GP One and Primary Care One is currently being implemented.  All the resources will shortly be available on the Centre’s website at: http://www.equalityhumanrights.wales.nhs.uk/resources

5.	Survey of General Practices

Between April and June 2018, the CEHR ran a survey for GP practice staff to understand what works well, what barriers exist, and what could help to improve the experience for patients with sensory loss.  91 questionnaires were completed.  A separate report will be published with a full analysis but below is a summary of the key findings:

- 45% of those surveyed had heard of the All Wales Standards for Accessible Communication and Information for People with Sensory Loss;

- 47% said their surgery currently records information about the communication and/or information needs of their patients;

- 88% hold this information in their IT system.

- 63% said they don’t experience any difficulties in finding out about or recording their patients’ communication or information needs.

- Of those who had heard of the all Wales Standards, 26% felt that the Standards had helped improve access to healthcare for people with sensory loss since their launch in 2013; 34% were unsure;

- Disappointingly, only 20% of respondents had heard of the ‘It Makes Sense’ campaign;

- Of the 91 respondents, 84% said they had not undertaken the sensory loss e-learning module.

The survey findings will be used to develop a baseline for measuring the future impact of the Standard.  Patients will be included in future surveys and a question on ‘wayfinding’ will be included working with RNIB Cymru to develop the question.

6. Going Forward

The mandate to implement this work was issued to all health boards and trusts at the end of September 2018 in the form of a Welsh Health Circular, accompanied by an Implementation Plan.

Just over half of GP surgeries now have the technology to implement phase 2 of the project i.e. automatically including the recorded communication and/or information needs of patients with sensory loss in e-referrals to secondary care.  Work to enable this functionality to go ‘live’ in the remaining GP surgeries should be completed by December 2018.

This report captures the work undertaken to implement the Accessible Information Standard during 2017/18.  The Senior Officers group recently reviewed progress on implementing the All Wales Standards.  The Accessible Information Standard has great potential to improve the experience of patients with sensory loss.  However, there is still more work to do to make communication and information accessible to patients with sensory loss across primary and secondary healthcare. A number of issues were highlighted as priorities for going forward in 2019/20.  These include the need to:

- Offer different ways of contacting GP and hospital services, in particular, using email and two way text messaging;

- Develop greater awareness and understanding of the All Wales Standards in general practices;

- Increase the take up of the Sensory Loss e-learning module particularly in general practices;

- Focus more on engaging with people with sight loss and dual sensory loss;

- Review and/or establish clear processes for staff in general practices to book BSL Interpreters and ensure staff know how to book an interpreter;

- Review and develop the concerns process to ensure that it is accessible to people with sensory loss;

- Strengthen the NHS Outcomes Framework reporting measures to enable better scrutiny and more robust monitoring of progress in implementing the Standard;

- Share health information produced in accessible formats across NHS Wales to meet different communication needs and avoid duplicating work.

In better understanding the barriers faced by the sensory loss community in accessing healthcare and to get a fuller picture, the following links may prove useful:

Action on Hearing Loss Cymru: On the Record: Good Practice

Wales Audit Office report: Speak My Language

Marcia Morgan

Programme Manager for Accessible Information Standard

31st October 2018

Appendix 1

1.	Making Contact and/or Appointments

Across all the groups, individuals reported difficulties in arranging, changing or cancelling appointments with their surgery.  Many people were asked to telephone the surgery for appointments. For those who are D/deaf, hard of hearing or have dual sensory loss it is a problem. Minicom users reported difficulties in getting through on the telephone number and similarly, some Next Generation Text users found that the telephone was put down on them repeatedly.  A minority of people preferred to use a fax.

The majority of people had to attend the surgery in person to arrange an appointment even when feeling unwell, having no transport and needing to walk a considerable distance or use public transport.  A smaller number of people reported good experiences with surgeries who accepted appointments by text; a very small number of people had tried My Health Online, some with excellent results whilst others had given up due to issues with setting it up and receiving a password.  For those who are blind, have sight loss or dual sensory loss, My Health Online was not accessible.  Several people arranged appointments on the telephone via a family member or interpreter.

Across all the groups it was felt that the receptionist is often the biggest obstacle to accessing healthcare, both at the surgery and at the hospital.

Suggested Solutions

- Surgeries to have a mobile number so that appointments can be arranged, altered or cancelled by text and also, video calls/Skype/Facetime for those who are D/deaf or hard of hearing;

- Use of emails to arrange, change and cancel appointments for those who are D/deaf or hard of hearing;

- Staff awareness training on receiving minicom or Next Generation Text  calls – to prevent the telephone being put down on them;

- All staff in surgeries to have training on testing and using the hearing loop;

- A “live chat” option which would allow patients to chat online with the receptionist in order to book/change an appointment;

- All front line staff to undertake training on sensory loss.

2.	Making GP Surgeries aware of Communication and Information Needs

Most of the groups engaged with agreed that a card to show to receptionists would be really helpful.   The card might have a number of choices so that the individual can tick the ones that apply to them.  This would be particularly useful to those with dual sensory loss.  The groups were shown examples of different cards.

Suggested Solutions

- Develop cards with options for individuals to tick;

- Options to include individual preferences for example, requesting a male or female interpreter;

- Options to include whether an individual needs help with, for example, wayfinding;

- Include data codes on cards to help staff to input data on their computer system;

3.	Communication in the Surgery/with GP at Appointment

For people whose first language is BSL, the majority of people prefer to use the services of a face to face BSL interpreter when attending appointments.  Video interpreting was not their first choice as BSL is a 3D language.  People shared issues with interpreter bookings.  Bookings are requested and they are told that bookings have been made. However, an interpreter might not arrive at the appointment time.  It is then difficult to establish whether the interpreter could not attend for some reason or whether it was an issue with the booking.

Some people thought it would be helpful to have a note taker at appointments as lots of information is given especially with complicated diagnoses and this was not always easy to remember after the consultation had finished and for patients who may have dementia.

Where a surgery or hospital has an appointment screen in the waiting area, they do not necessarily have audio on them so people who are blind or have sight loss do not know that their name has flashed up on the screen.  For those with dual sensory loss they can neither see their name or hear it being called.  Where there is no screen, those who are deaf or hard of hearing do not hear their name being called.

Another issue raised across all the sensory loss groups but particularly with those with sight or dual sensory loss was the difficulty that quite a few had experienced where the consultant does not always explain to the patient what is happening both in terms of their treatment or their diagnosis.

Suggested Solutions

- Training for staff on how to book interpreters

- A robust system for interpreter bookings which includes notifying individuals of the name of the interpreter booked

- Having an ipad/tablet available in every surgery.  If there is no face-to-face interpreter available, it may be possible to use video interpreting service.  This would also be helpful for emergency appointments which are arranged at short notice;

- Consistency – it would help with continuity and confidentiality for ongoing conditions if the same interpreter was involved in follow up/further appointments;

- People also said they would be happy to text and check with their preferred interpreter to assist the surgery in making arrangements;

- Appointment screens need to have audio.  Where there is no screen someone needs to let the patient know it’s their turn.

- Again where there is no screen a buzzer could be given to the patient when they arrive for the appointment which would vibrate to let them know when its their turn.

- All health professionals to undertake the sensory loss training module under the ‘Treat Me Fairly’ suite of training modules.

4.	Requesting a BSL Interpreter

It was disappointing to find that some of those who need to use a BSL interpreter were not aware that they could request an interpreter for optician appointments and dental appointments.

Suggested Solution

- While outside the scope of this project, patients need to be more aware of their rights under the Equality Act 2010 and this is where the third sector could help.

5.	Raising a Concern or Complaint

Most of the groups were unaware of the Putting Things Right Process (PTR) and would not use it to report any issues that they had in communicating with their GP surgery.  For those whose first language is not English, it was identified that the The Putting Things Right (PTR) process is inaccessible.

Suggested Solutions

- The PTR process needs to be made accessible to Deaf people and all of the sensory loss community.  Resources in a variety of formats, including (but not limited to) audio and BSL need to be developed;

- Template letters may be a useful tool to provide a route into the complaints process but these need to be fully accessible, not just to those who use BSL but particularly to those who are blind or have sight loss;

- Touch screen – a feedback method at the end of the appointment – this could include communication needs feedback – instant feedback which may feel less formal.

6.	Mandatory Training

Many of the groups asked ‘Why can’t the sensory loss training module under Treat Me Fairly be made mandatory’?  This particular question started quite a debate at the Regional Network meeting of the Wales Council of the Blind.

Suggested Solution

- Although not mandatory, at every engagement meeting where the Centre met with health professionals, the benefit of the training was highlighted and encouraged. General practices need to be made aware of the module and how to access it.

7. 	Engagement through Centre of Sign, Sight and Sounds (CoS)

COS were commissioned to design and produce a set of resources to help raise awareness of the Accessible Information  Standard.  As part of this work, they were asked to consult with various members of the Sensory Loss Community in North Wales.

As this is a Community who rely on both signed and spoken communication, the consultations were carried out on a group basis via a conversation.

Groups consulted included members of the North Wales Deaf Community and the Visually Impaired Community, both in the offices of COS in Colwyn Bay and at various external group settings.

100% of the people spoken to thought the Standards were a good idea in principle, but many were concerned that their primary care Health Professionals would not pay heed to them.

Some of the comments received during the period of engagement were:

“Brilliant news, we won’t have to tell them every time”

“Does this mean they will automatically book an interpreter without us telling them?”

“Sounds good but will they actually look at the information”

“My GP won’t bother”

With regard to the materials produced as part of the resources commissioned, various other organisations were consulted including Wales Council for Blind People and RNIB, as well as members of the Community about the design of the poster/leaflet, concentrating on the colour and font so that it matched the general rules of production for people with a visual impairment.

Additionally, COS consulted with a group of interpreters and with BSL users to get their feedback about the video produced.  It was felt that the BSL video was clear and explained what they needed to do.

The poster/leaflet was well received, although some people did question the use of yellow as the background.  It was explained that for some people, depending on their sight loss, a yellow background made the resource visually better.  It was further explained that a suite of resources were being designed to ensure that they were fully accessible to all of the sensory loss community.  It was never the intention to create one set of resources and hope that they suited everyone.

8.	Wayfinding

One issue in particular which was raised by the sight loss community was the accessibility of the built environment i.e. surgery lay out, touch screen check-in, wayfinding challenges, not being guided to a consulting room etc.  We are aware that this is something that came up a lot in research RNIB developed earlier in the year.

4.	Key Messages

There were three key messages the Centre asked the groups to observe with all future interactions with health professionals to ensure the success of The Standard, taken from the ‘It Makes Sense’ campaign, these are:

Tell doctors, nurses, paramedics and other health professionals how you prefer to communicate

Ask to receive information in the format you prefer, including BSL, large print, electronic or Braille

Share your concerns if you do not receive this.